## Overview
LeadDesk Mini — Task A & Task B Delivery Plan
Plan principle | Finish and deploy Task A before creating any Task B branch.
Task A scope | Public lead form + MongoDB persistence + unprotected /admin lead management.
Task A branches | 9
Task B branches | 8
Task B scope | Real admin login, protected routes/APIs, security hardening, deployment and walkthrough.
Clean Git workflow — repeat for every row
1 | Sync main | git switch main | git pull --ff-only | git status --short | Must be empty
2 | Create branch | git switch -c <branch> | Use exact branch from plan |  | One concern only
3 | Implement | Small logical commits | Never commit secrets | Keep design references unchanged | Run local checks
4 | Verify | npm run typecheck | npm run lint | npm test | npm run build
5 | Open PR | Use supplied PR title | Paste supplied PR message | Attach screenshots when UI changes | Review diff
6 | Merge & clean | Squash merge | Delete remote branch | Delete local branch | Sync clean main
Boundary rule: no login, users, sessions, protected routes or auth UI may enter Task A. Task B begins only after Task A is merged, deployed and accepted.

## Task A Plan
Seq | Git Branch | Depends On | Design Reference | Features Added | How To Use Design | Acceptance Metrics | PR Title | PR Message
1 | chore/task-a-foundation | main | leaddesk_mini_design_system/DESIGN.md; all Stitch screens | Next.js/TypeScript foundation, MongoDB driver, Zod, lint/build scripts, environment template, module folders | Use DESIGN.md only for tokens and naming. Do not build login or secured routes in Task A. | Fresh install succeeds; typecheck, lint and production build pass; .env files and secrets are ignored; no auth module or login route exists. | chore(task-a): establish LeadDesk full-stack foundation | ## Summary - scaffold the Next.js application - configure TypeScript, linting and MongoDB environment contracts - create domain-oriented module boundaries ## Validation - npm run typecheck - npm run lint - npm run build
2 | feat/task-a-leads-data | chore/task-a-foundation | No page screenshot; leaddesk_mini_design_system/DESIGN.md for domain terminology | MongoDB leads collection, schema validation, indexes, Lead types, repository, service, mapping, database setup script | Translate UI labels into stable values: new/contacted/closed and four budget-range keys. Keep persistence independent of React components. | Database setup is idempotent; malformed documents are rejected; default status is new; status/createdAt and email indexes exist; repository exposes no MongoDB document outside the service. | feat(task-a): add MongoDB lead data module | ## Summary - add the leads collection and database validator - add indexed repository queries and DTO mapping - document the Task A data model ## Validation - npm run db:setup - npm run typecheck - npm run build
3 | feat/task-a-lead-api | feat/task-a-leads-data | landing_page_form_errors; landing_page_form_states_submitting_success; landing_page_server_error | POST /api/leads, shared Zod validation, normalized API responses, same-origin check, safe errors | Use the form-state screens to define response states and field error keys. Backend messages must support the exact inline UI without leaking MongoDB errors. | Valid lead returns 201 and persists; invalid name/email/budget/message returns 422 with field errors; server failures return a generic retryable response; status and timestamps cannot be supplied by the browser. | feat(task-a): add validated public lead submission API | ## Summary - expose POST /api/leads - validate and normalize every submission server-side - return UI-ready success and error contracts ## Validation - valid submission persists - tampered budget is rejected - internal errors are not exposed
4 | feat/task-a-public-ui | feat/task-a-lead-api | landing_page_refined; landing_page_desktop; landing_page_mobile; leaddesk_mini_design_system/DESIGN.md | Responsive landing page, navigation, hero, trust strip, process, services, contact form shell and footer | Treat landing_page_refined as the desktop source of truth, landing_page_mobile for breakpoints, and DESIGN.md for Geist typography, colors, spacing and radii. Convert static HTML into reusable React components. | Matches reference hierarchy at 1440px and 390px; CTA scrolls to the form; labels remain visible; no horizontal overflow at 360px; keyboard focus is visible; admin link goes directly to /admin without login. | feat(task-a): implement responsive public landing page | ## Summary - translate the approved Stitch landing page into React - add responsive navigation and content sections - apply the LeadDesk design tokens ## Validation - verify 360px, 390px, tablet and desktop layouts - verify keyboard navigation - npm run build
5 | feat/task-a-form-states | feat/task-a-public-ui | landing_page_form_errors; landing_page_form_states_submitting_success; landing_page_server_error | Client validation, API submission, disabled/loading state, success confirmation, preserved-values server error, accessible announcements | Reuse the default form from the refined landing page. Apply error layout from form_errors, success/submitting treatment from form_states, and retry panel from server_error without changing surrounding page geometry. | Client and server validation agree; first invalid field is focusable; duplicate submission is blocked; success clears the form and shows confirmation; failure preserves values and permits retry; status is announced accessibly. | feat(task-a): connect lead form and complete submission states | ## Summary - connect the public form to POST /api/leads - implement validation, loading, success and retry states - preserve accessible focus and announcements ## Validation - test valid and invalid submissions - test duplicate-click prevention - test recoverable server failure
6 | feat/task-a-admin-api | feat/task-a-leads-data | admin_dashboard_populated; admin_dashboard_details_states; admin_dashboard_empty_unauthorized (empty state only) | GET lead list, search, status filter, sort, pagination, GET lead details, PATCH status endpoint and dashboard counts | Use table columns and filters from the populated dashboard to determine the API projection. Use detail-drawer fields from details_states. Do not add authentication or authorization yet. | Search covers name/email/message; status filter and newest/oldest sort combine correctly; pagination metadata and counts are accurate; invalid IDs return 404; only new/contacted/closed are accepted; updates persist after reload. | feat(task-a): add lead administration APIs | ## Summary - expose list, search, filter and detail APIs - add persistent status updates and dashboard counts - keep Task A admin endpoints intentionally unprotected ## Validation - exercise search/filter/sort combinations - verify 404 and invalid-status handling - verify persistence after refresh
7 | feat/task-a-admin-ui | feat/task-a-admin-api | admin_dashboard_refined; admin_dashboard_populated; admin_dashboard_details_states; admin_dashboard_empty_unauthorized; admin_flow_mobile | /admin dashboard, summary cards, search, filters, responsive table/cards, status control, lead details drawer, loading/empty/no-results/error/toast states | Use admin_dashboard_refined as desktop authority, populated for table density, details_states for the drawer and fallbacks, empty_unauthorized only for its empty panel, and admin_flow_mobile for card transformation. Omit login/logout/lock UI. | New leads appear without reload after refetch; search and filters map to URL/query state; status change persists and shows success/failure feedback; empty database differs from no results; mobile has no table overflow; /admin opens without authentication. | feat(task-a): implement lead management dashboard | ## Summary - build the responsive /admin dashboard - connect search, filtering, details and status updates - implement loading, empty, no-results and failure states ## Validation - verify desktop table and mobile cards - verify persistent status changes - verify all fallback states
8 | test/task-a-complete-flow | feat/task-a-form-states + feat/task-a-admin-ui | All Task A screens; system_error_pages for generic fallback styling | Unit tests for validation/service logic, API integration coverage, public-to-admin smoke flow, responsive/accessibility review, Task A README and screenshots | Use screenshots as visual QA targets, not as pixel-copy requirements. Use system_error_pages only for generic 404/500 language and visual consistency. | Form submission appears in /admin; search finds it; all three statuses persist; fresh build passes; no console errors; mobile and keyboard flows work; README documents data model, setup, URLs and Task A scope; Git status is clean. | test(task-a): verify complete LeadDesk lead workflow | ## Summary - cover the public-to-admin Task A journey - verify validation, persistence, search and status updates - complete Task A documentation and visual QA ## Validation - npm run typecheck - npm run lint - npm test - npm run build - manual fresh-browser smoke test
9 | chore/task-a-deployment | test/task-a-complete-flow | No direct UI reference; deployment must preserve all approved Task A screens | MongoDB Atlas production configuration, Vercel environment variables, database setup, live smoke test and Task A URLs | Make no visual changes except deployment fixes. Do not add login because that belongs to Task B. | Landing page and /admin load from fresh browser; submission, search and status updates work against production MongoDB; no localhost or secrets are committed; health endpoint succeeds; deployment URL is documented. | chore(task-a): deploy and verify LeadDesk Mini | ## Summary - configure production MongoDB and Vercel - run the database setup safely - document and verify Task A URLs ## Validation - fresh-browser production smoke test - confirm persisted status after refresh - confirm repository contains no secrets
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task A: execute branches in sequence. Each row should become one focused squash-merged PR.

## Task B Plan
Seq | Git Branch | Depends On | Design Reference | Features Added | How To Use Design | Acceptance Metrics | PR Title | PR Message
1 | feat/task-b-auth-data | Task A merged and deployed | No page screenshot; admin_login_desktop defines fields and remember-session behavior | Users and sessions collections, unique normalized admin email, password hashing, opaque session-token hashes, TTL index, idempotent admin seed | Use login fields to define auth inputs, but keep password/session logic fully server-side. Extend modules without changing the leads repository. | Passwords are never stored or logged; sessions expire automatically and are rejected immediately when expired; raw session tokens never enter MongoDB; admin seed is environment-driven and idempotent. | feat(task-b): add admin identity and session persistence | ## Summary - add users and database-backed sessions - hash passwords and opaque session tokens - add TTL cleanup and idempotent admin provisioning ## Validation - seed admin twice without duplicates - verify password hash storage - verify expired session rejection
2 | feat/task-b-auth-api | feat/task-b-auth-data | admin_login_desktop; system_error_pages | Login, logout and current-session APIs; secure HttpOnly cookie; generic credential error; optional remembered session; login audit/rate-limit behavior | Map invalid and expired states to the alerts shown in admin_login_desktop. Use generic system language and never reveal whether an email exists. | Correct credentials create a server session; incorrect credentials return a generic 401; cookie is HttpOnly, Secure in production and SameSite; logout revokes the database session; no token is exposed to client JavaScript. | feat(task-b): add secure admin authentication APIs | ## Summary - implement login, logout and session endpoints - issue secure opaque-session cookies - normalize credential and expiry errors ## Validation - test valid and invalid login - verify cookie attributes - verify logout revokes server session
3 | feat/task-b-login-ui | feat/task-b-auth-api | admin_login_desktop; leaddesk_mini_design_system/DESIGN.md | /login page, email/password form, reveal-password control, loading state, invalid-credentials alert, expired-session alert, return-to-site link | Translate admin_login_desktop directly into React using shared design tokens. Preserve the centered 440px card and atmospheric background. Do not add public registration. | Valid login redirects to the intended admin URL; incorrect credentials preserve email but clear password; session-expired message is distinguishable; loading blocks duplicate submit; form works by keyboard and on 360px screens. | feat(task-b): implement admin login experience | ## Summary - build the approved /login interface - connect authentication and redirect behavior - implement invalid and expired-session states ## Validation - keyboard and mobile checks - duplicate-submit prevention - valid and invalid credential flows
4 | feat/task-b-admin-protection | feat/task-b-login-ui | admin_dashboard_refined; admin_dashboard_empty_unauthorized (unauthorized state); admin_flow_mobile | Protect /admin and all admin APIs, server-side session verification, redirect with return URL, authenticated user menu, logout action, unauthorized fallback | Keep the Task A dashboard visually unchanged. Add identity/logout only where shown by the admin references. Use the unauthorized half of empty_unauthorized for access-denied rendering. | Fresh browser cannot access admin page or data APIs; login returns to requested admin URL; disabled/deleted users lose access; logout blocks back-navigation data access; public POST /api/leads remains available. | feat(task-b): protect admin routes and lead operations | ## Summary - require server-verified sessions for /admin and admin APIs - add safe redirect and logout behavior - preserve the public lead endpoint ## Validation - test direct unauthenticated page/API access - test login return URL - test logout and disabled-user behavior
5 | feat/task-b-security-hardening | feat/task-b-admin-protection | system_error_pages; landing_page_server_error; existing admin failure states | Same-origin/CSRF enforcement, login throttling, session rotation/revocation, sanitized logs, security headers, production-secret audit and audit events | Reuse existing fallback visual language; security failures should be calm and actionable. Do not expose implementation or database details. | Cross-origin state changes are rejected; repeated login failures are throttled; private keys and hashes never reach logs/browser bundle; sessions can be revoked; protected errors reveal no lead data; security headers are present. | security(task-b): harden authentication and admin access | ## Summary - add request-origin and abuse protections - tighten session lifecycle and security headers - audit secrets, logs and protected responses ## Validation - cross-origin mutation test - throttled-login test - browser bundle and log secret audit
6 | test/task-b-auth-flow | feat/task-b-security-hardening | admin_login_desktop; admin_dashboard_refined; admin_dashboard_empty_unauthorized; system_error_pages | Authentication unit/integration tests, fresh-browser end-to-end flow, expired session, logout, unauthorized API, regression coverage for Task A | Use approved screens as visual targets for login, expiry and unauthorized states. Confirm Task B changes do not alter public landing/form behavior. | Fresh incognito browser redirects /admin to /login; test credentials work; session persists through refresh; expiry and logout remove access; unauthorized API calls return 401/403; Task A submission/search/status regression passes. | test(task-b): verify secure admin workflow | ## Summary - cover login, protected access, expiry and logout - verify fresh-browser behavior - rerun the complete Task A lead workflow ## Validation - npm run typecheck - npm run lint - npm test - npm run build - incognito end-to-end test
7 | docs/task-b-readme-loom | test/task-b-auth-flow | All final screens; no new visual design | README architecture/auth/data-model sections, local and production setup, live URLs, safe test-credential delivery note, Loom script/link, AI-use disclosure | Use screenshots only to explain the working flow. Do not place the real test password in the public repository; deliver credentials privately. | README reproduces setup from a clean clone; auth and authorization are explained separately; data model is documented; live URLs work; Loom demonstrates form submission → login → search → status update → logout within about three minutes. | docs(task-b): complete deployment and walkthrough documentation | ## Summary - document data model, authentication and deployment - add final URLs, screenshots and Loom walkthrough - add the required AI-use disclosure ## Validation - follow README from a clean clone - verify all public links - confirm no credentials or secrets are committed
8 | chore/task-b-production-release | docs/task-b-readme-loom | No direct UI reference; final deployment must preserve all Task A and B screens | Production migration for auth collections/indexes, assessment admin provisioning, deployment verification, final release tag | Make deployment-only changes. Preserve Task A URLs and visual behavior. | Fresh browser completes the full flow; test credentials work; /admin and APIs are protected; public lead submission remains open; session/logout behavior works in production; repository and main branch are clean; final tag points to verified commit. | chore(task-b): release secure LeadDesk Mini | ## Summary - provision production auth storage and assessment admin - deploy the secured application - tag the verified submission release ## Validation - complete fresh-browser Task A + Task B flow - verify credentials privately - confirm clean main and release tag
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task B: execute branches in sequence. Each row should become one focused squash-merged PR.